## Identified Deficiencies
| DEFICIENCY/OBSERVATION (inspection recommendation #) | CORRECTIVE MEASURE
1 | Control / remove phragmites. | Phragmites is sprayed twice per year.
2 | Small potholes / ruts were present at the crest. | Filling and grading completed.
3 | The swale between the toe of the embankment and coal pile has ponding water. | Regraded swale to create positive draining towards outfall to eliminate ponding water.
4 | Silt was observed in the primary spillway's concrete flared end section at the toe of the embankment. | Removed silt from pipe outlet.
5 | Sloughing was observed in two areas of the recently constructed buttress. | Regraded and reseeded general area and utilized turf reinforcing matting to promote stabilization.
6 | Sparse vegetation was observed in areas of the recently constructed buttress. | Regraded and reseeded areas.